## Team
Scrum
Member | Role | Email
Jürgen Vogel | Product owner | juergen.vogel@bfh.ch
Pira Mahendran | Scrum master | mahep1@bfh.ch
Stefan Johner | Developer | johns2@bfh.ch
Amin Ghodrati | Developer | ghodm1@bfh.ch
Michel Murbach | Developer | murbm1@bfh.ch
Sabine Martin | Developer | marts1@bfh.ch
Riza Ramsauer | Developer | ramsr4@bfh.ch
Scrum meetings | Time | Room
Wednesday | 16:15 | N421
Thursday | 14:25 | N522
Friday | 14:25 | 308

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login | Only authorized user can login, unauthorized not. | high | 20h | 25h | 15h | finished
2 | Forgot password | Renew the password with authorized email address | medium | 10h |  | 0h | waiting
3 | Add patient | User add a new patient (connect to database) | high | 15h | 15h | 15h | finished
4 | View therapy/tasks/medication | User is able to view a new therapy/ tasks/ medication (connect to database) | high | 15h | 15h | 15h | finished
5 | Add a medication | User add a new medication plan | high | 15h | 8h | 8h | working in progress
6 | Notification | User should obtain notification: Well Done, Correction/Reminder, Alert | high | 30h | 20h | 20h | working in progress
7 | Medication info search | User wants search external info about the medication | medium | 15h | 8h | 8h | working in progress
8 | Therapy/ task info search | User wants search external info about therapy/ task | medium | 10h | 10h | 10h | finished
9 | Update the task | User wants see the progress | high | 10h | 5h | 5h | working in progress
10 | Create a report | User wants to get/ to see the report at the end | high | 20h |  | 0h | waiting
11 | Information about the patient | Get patient summary info | medium | 10h | 5h | 5h | working in progress
12 | Information about the doctor | Get external info about the doctor/ hospital | low | 10h |  | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status | User Story
2.1 | 1 | GUI Medication | Design GUI for Medication | Home View | Sabine | high | 10 | 8 | 8 | finished | Medication
3.1 | 1 | GUI Therapy | Design GUI for Therpy | Home View | Michel | high | 10 | 8 | 8 | finished | Therapy
1.1 | 1 | Init | Implement Vaadin Init Class | Init Class | Riza | high | 5 | 8 | 8 | finished | Login
1.2 | 1 | GUI Login | Design GUI for login | Login View | Pira | high | 5 | 5 | 5 | finished
1.3 | 1 | GUI home site | Design GUIs for the home site | Home View | Amin | high | 5 | 5 | 5 | finished
1.4 | 1 | User Model | Implement User Model with credentials (dummy data) | Model | Stefan | high | 5 | 3 | 3 | finished
1.6 | 1 | Login and Home Controller | Implement the controller for Login and function desicion | Controller | Pira | high | 5 | 5 | 5 | finished
1.7 | 1 | Merge Components | Merge the implemented code | UI / controller / models | Amin | high | 5 | 5 | 5 | finished
1.8 | 1 | User Database | Implement Database with login data | Model / Database | Riza | low | 5 | 2 | 2 | finished
|  | Sub total |  |  |  |  | 55 | 49 | 49
2.1 | 2 | GUI for the view of therapy/ task | Create GUI for the therapy/ task tool | Therapy View | Michel | high | 5 | 5 | 5 | finished | View therapy/tasks/medication
2.2 | 2 | GUI for view of the medication | Create GUI for the medication tool | Medication View | Sabine | high | 5 | 5 | 3 | work in progress
2.3 | 2 | GUI for the info search therapy | Create GUI for the therapy info | Therapy View | Michel | low | 5 | 5 | 5 | work in progress
2.4 | 2 | GUI for the info search medication | Create GUI for the medication info | Medication View | Sabine | low | 5 | 5 | 6 | work in progress
2.5 | 2 | Login session handling | Implement session handling for login | Login View / Controller / Auth Model | Stefan | high | 5 | 5 | 8 | finished | Login
2.6 | 2 | Controller for therapy | Implement therapy controller with state pattern | Therapy Controller | Stefan | high | 5 | 5 | 3 | work in progress | Therapy
| 2 | Database implementation (dummy XML) | XML's for Patients, Therapies, Medication | XML Files and Schema | Riza | low | 10 | 10 | 8 | finished
2.8 | 2 | GUI main design | Implement main design (colors, responsive design, icons) | All Views | Amin | high | 10 | 10 | 10 | work in progress
2.9 | 2 | Model for medication and therapy | Implement models for medication and therapy views | Medication Model / Therapy Model | Pira | high | 10 | 10 | 10 | finished
|  |  | Implement DB Controller and Model | DB Controller / DB Model | Stefan | high | 0 | 2 | 2 | work in progress
2.10 |  | Sub total |  |  |  |  | 60 | 62 | 60
| 3 | Communication with Database | Implement DB Controller and Model | DB Controller / DB Model | Stefan | high | 5 | 4 | 0 | work in progress | Add patient
|  |  | Implement therapy controller with state pattern | Therapy Controller | Stefan | high | 0 | 3 | 0 | work in progress
|  |  | Create GUI for the medication tool | Medication View | Sabine | high | 0 | 3 | 0 | work in progress | Add a medication
|  |  | Create GUI for the therapy info | Therapy View | Michel | low | 0 | 2 | 0 | work in progress
2.7 |  |  | Create GUI for the medication info | Medication View | Sabine | low | 0 | 3 | 0 | work in progress
|  |  | Implement main design (colors, responsive design, icons) | All Views | Amin | high | 0 | 5 | 0 | work in progress
|  |  | Tester classes | All Views | Michel | low | 18 | 2 | 0 | waiting
|  |  | Back Buttons in all GUI Views | All Views | Michel | high | 2 | 2 | 0 | work in progress
|  |  | Patient summary report in GUI HomeView | Home View | Pira | high | 10 | 12 | 0 | work in progress
|  |  | Revise exception handling | All Views | Stefan | medium | 15 | 16 | 0 | work in progress
|  |  | Daily medication | Medication View | Sabine | high | 10 | 12 | 0 | work in progress
[7 empty] | 60 | 64 | 0
Note on L2: Stefan Johner: Zuordnung der User Stories noch überarbeiten!

## Burndown Chart
Burndown chart
|  | Burned down |  | Balance |  | Weekly Completed
Date | Week | Planned | Actual | Planned | Actual
KW47 | 0 | 0 | 0 | 180 | 180 | 0
KW48 | 1 | 30 | 21 | 150 | 159 | 21
KW49 | 2 | 30 | 21 | 120 | 138 | 21
KW50 | 3 | 30 | 20 | 90 | 118 | 20
KW51 | 4 | 30 | 20 | 60 | 98 | 20
KW52 | 5 | 0 | 13 | 60 | 85 | 13
KW1 | 6 | 0 | 30 | 60 | 55 | 30
KW2 | 7 | 30 | 20 | 30 | 35 | 20
KW3 | 8 | 30 | 35 | 0 | 0 | 35
Grafik
Hours
Weeks

## Sprint Backlog_all_old
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | GUI Login | Create GUI for login | Start View | Sabine/ Riza | high | 10 |  | 0 | waiting
1.2 | 1 | GUI home site | Create GUIs for the home site | Main View | Sabine/ Riza | high | 10 |  | 0 | waiting
1.3 | 1 | Patient-Doctor-Notification | Implementation and Definition of classes | Models | Michel/ Stefan | high | 8 |  | 0 | waiting
1.4 | 1 | Therapy-Task-Medication | Implementation and Definition of classes | Models | Michel/ Amin | high | 4 |  | 0 | waiting
1.5 | 1 | UI Controller | Implementation of controller | Controller | Michel/ Amin | high | 8 |  | 0 | waiting
1.6 | 1 | GUI home site Navigator | Implementation of view navigator | View Navigator | Pira/ Amin | high | 8 |  | 0 | waiting
1.7 | 1 | Merge MVC Classes | Merging and test of the created classes | UI, controller, navigator, models | Pira/ Stefan | high | 12 |  | 0 | waiting
2.1 | 2 | GUI for the view of therapy/ task | Create GUI for the therapy/ task tool | Therapy Window | Pira | high | 5 |  | 0 | waiting
2.2 | 2 | GUI for view of the medication | Create GUI for the medication tool | Medication Window | Stefan | high | 5 |  | 0 | waiting
2.3 | 2 | GUI for the notifiactions | Create GUI for the notification Well done, advice/ reminder, alert | Notification View | Amin/Riza | high | 18 |  | 0 | waiting
2.4 | 2 | GUI for the info search therapy | Create GUI for the therapy info | Therapy Window | Sabine | high | 9 |  | 0 | waiting
2.5 | 2 | GUI for the info search medication | Create GUI for the medication info | Medication Window | Michel | high | 9 |  | 0 | waiting
2.6 | 2 | Comment | Java Doc | all | all | low | 1 |  | 0 | waiting
2.7 | 2 | Test | Testing | all | Pira/Stefan | high | 8 |  | 0 | waiting
3.1 | 3 | XML Schema patient | Create XML-File and Schema for the patient data | Database | Pira | medium | 4 |  | 0 | waiting
3.2 | 3 | XML Schema therapy | Create XML-File and Schema for the therapy data | Database | Sabine/Riza | medium | 8 |  | 0 | waiting
3.3 | 3 | XML Schema medication | Create XML-File and Schema for the medication data | Database | Stefan | medium | 4 |  | 0 | waiting
3.4 | 3 | read and update the report | read and update (override) the actual XML report | Database | Amin | medium | 18 |  | 0 | waiting
3,4,1 | 3 | external therapy info | Search external info for the specific therapy | Search Window /Database | Michel | low | 8 |  | 0 | waiting
3,5,1 | 3 | external medication info | Search external info for the specific medication | Search Window /Database | Sabine/Riza | low | 8 |  | 0 | waiting
3.6 | 3 | Summary about the patient | Get the summary about the actual patient therapy | Summary Window/ Database | Pira/Stefan | medium | 8 |  | 0 | waiting
3.8 | 3 | Comment | Java Doc | all | all | low | 0.5 |  | 0 | waiting
3.9 | 3 | Test | testing | all | all | high | 1.5 |  | 0 | waiting