## Team
Scrum
Member | Role | Email
Jürgen Vogel | Product owner | juergen.vogel@bfh.ch
Pira Mahendran | Scrum master | mahep1@bfh.ch
Stefan Johner | Developer | johns2@bfh.ch
Amin Ghodrati | Developer | ghodm1@bfh.ch
Michel Murbach | Developer | murbm1@bfh.ch
Sabine Martin | Developer | marts1@bfh.ch
Riza Ramsauer | Developer | ramsr4@bfh.ch
Scrum meetings | Time | Room
Wednesday | 16:15 | N421
Thursday | 14:25 | N522
Friday | 14:25 | 308

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login success | Only authorized user can login | high | 10h |  | 0h | waiting
2 | Login rejection | Unauthorized user can not to login | high | 10h |  | 0h | waiting
3 | Forgot password | Renew the password with authorized email address | medium | 10h |  | 0h | waiting
4 | Add patient | User add a new patient (connect to database) | high | 15h |  | 0h | waiting
5 | Add therapy/tasks/medication | User add a new therapy/ tasks/ medication (connect to database) | high | 15h |  | 0h | waiting
6 | Add a medication | User add a new medication plan | high | 15h |  | 0h | waiting
7 | Notification | User should obtain notification: Well Done, Correction/Reminder, Alert | high | 30h |  | 0h | waiting
8 | Medication info search | User wants search external info about the medication | medium | 15h |  | 0h | waiting
9 | Therapy/ task info search | User wants search external info about therapy/ task | medium | 15h |  | 0h | waiting
10 | Update the task | User wants see the progress | high | 15h |  | 0h | waiting
11 | Create a report | User wants to get/ to see the report at the end | high | 20h |  | 0h | waiting
12 | Information about the patient | Get patient summary info | medium | 10h |  | 0h | waiting
13 | Information about the doctor | Get external info about the doctor/ hospital | low

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | GUI Login | Create GUI for login | Start Window | Sabine/ Riza | high | 10 |  | 0 | waiting
1.2 | 1 | GUI home site | Create GUIs for the home site | Main Window | Sabine/ Riza | high | 10 |  | 0 | waiting
1.3 | 1 | Patient-Doctor-Notification | Implementation and Definition of classes | Models | Michel/ Stefan | high | 8 |  | 0 | waiting
1.4 | 1 | Therapy-Task-Medication | Implementation and Definition of classes | Models | Michel/ Amin | high | 4 |  | 0 | waiting
1.5 | 1 | UI Controller | Implementation of controller | Controller | Michel/ Amin | high | 8
1.6 | 1 | home site Navigator | Implementation of navigator | Navigator | Pira/ Amin | high | 8 |  | 0 | waiting
1.7 | 1 | Merge MVC Classes | Merging and test of the created classes | UI, controller, navigator, models | Pira/ Stefan | high | 12 |  | 0 | waiting
2.1 | 2 | GUI for the view of therapy/ task | Create GUI for the therapy/ task tool | Therapy Window | Pira | high | 5 |  | 0 | waiting
2.2 | 2 | GUI for view of the medication | Create GUI for the medication tool | Medication Window | Stefan | high | 5 |  | 0 | waiting
2.3 | 2 | GUI for the notifiactions | Create GUI for the notification Well done, advice/ reminder, alert | Notification View | Amin/Riza | high | 18 |  | 0 | waiting
2.4 | 2 | GUI for the info search therapy | Create GUI for the therapy info | Therapy Window | Sabine | high | 9 |  | 0 | waiting
2.5 | 2 | GUI for the info search medication | Create GUI for the medication info | Medication Window | Michel | high | 9 |  | 0 | waiting
2.6 | 2 | Comment | Java Doc | all | all | low | 1 |  | 0 | waiting
2.7 | 2 | Test | Testing | all | Pira/Stefan | high | 8 |  | 0 | waiting
[9 empty] | 0 | waiting
3.1 | 3 | XML Schema patient | Create XML-File and Schema for the patient data | Database | Pira | medium | 4 |  | 0 | waiting
3.2 | 3 | XML Schema therapy | Create XML-File and Schema for the therapy data | Database | Sabine/Riza | medium | 8 |  | 0 | waiting
3.3 | 3 | XML Schema medication | Create XML-File and Schema for the medication data | Database | Stefan | medium | 4 |  | 0 | waiting
3.4 | 3 | read and update the report | read and update (override) the actual XML report | Database | Amin | medium | 18 |  | 0 | waiting
3,4,1 | 3 | external therapy info | Search external info for the specific therapy | Search Window /Database | Michel | low | 8 |  | 0 | waiting
3,5,1 | 3 | external medication info | Search external info for the specific medication | Search Window /Database | Sabine/Riza | low | 8 |  | 0 | waiting
3.6 | 3 | Summary about the patient | Get the summary about the actual patient therapy | Summary Window/ Database | Pira/Stefan | medium | 8 |  | 0 | waiting
3.8 | 3 | Comment | Java Doc | all | all | low | 0.5 |  | 0 | waiting
3.9 | 3 | Test | testing | all | all | high | 1.5 |  | 0 | waiting

## Burndown Chart
Burndown chart
|  | Burned down |  | Balance |  | Daily Completed
Date | Day | Planned | Actual | Planned | Actual
2014-11-26 | 0 | 0 | 0 | 180 | 180 | 0
| 1 | 2 | 3 | 178 | 177 | 3
| 2 | 3 | 3 | 175 | 174 | 3
| 3 | 5 | 3 | 170 | 171 | 3
| 4 |  |  |  | #N/A | #N/A
| 5 |  |  |  | #N/A | #N/A
| 6 |  |  |  | #N/A | #N/A
| 7 |  |  |  | #N/A | #N/A
| 8 |  |  |  | #N/A | #N/A
| 9 |  |  |  | #N/A | #N/A
| 10 |  |  |  | #N/A | #N/A
| 11 |  |  |  | #N/A | #N/A
| 12 |  |  |  | #N/A | #N/A
| 13 |  |  |  | #N/A | #N/A
| 14 |  |  |  | #N/A | #N/A
| 15 |  |  |  | #N/A | #N/A
| 16 |  |  |  | #N/A | #N/A
| 17 |  |  |  | #N/A | #N/A
| 18 |  |  |  | #N/A | #N/A
| 19 |  |  |  | #N/A | #N/A
| 20 |  |  |  | #N/A | #N/A
Grafik
Hours
Days